## Start
The STR Ledger
Rehab Budget + ROI
Track every line. Project the lift. Know your payback.
ACQ-006 · v1.0 · DEMO
PROJECT AT A GLANCE
BUDGET (EST) | SPENT (ACTUAL) | VARIANCE % | 5-YR ROI
Log every line item — estimate vs actual, contractor, payment status, capex/repair tag. The Cost Allocation tab rolls it up by category and shows where dollars went. ROI Projection turns rehab spend into a year-1 revenue lift and a payback-period number you can defend.
1) Set property + dates on Settings. 2) Add lines on Budget Detail (estimate first; actual once paid). 3) Watch Variance % — red >+15% means you're over. 4) Cost Allocation auto-rolls by category, splits Capex/Repair for tax.
Capex vs Repair classification matters for tax. Pair this with Cost Segregation DIY (TAX-010) to claim accelerated depreciation.
Questions? hello@thestrledger.com
ACQ-006 · v1.0 · DEMO · Free updates forever

## Budget Detail
BUDGET DETAIL
Log every rehab line. Variance is auto-calculated. Capex/Repair drives tax treatment downstream.
Line # | Category | Description | Estimate | Actual | Variance | Var % | Contractor | Status | Capex/Repair | Notes
1 | Demolition | Kitchen demo + haul-off | 1800 | 2100 |  |  | ABC Demo Co | Paid in full | Repair
2 | Demolition | Bath 1 + 2 demo | 1400 | 1500 |  |  | ABC Demo Co | Paid in full | Repair
3 | Plumbing | Bath 1 rough-in + fixtures | 3200 | 3400 |  |  | Smokies Plumbing | Paid in full | Capex
4 | Plumbing | Bath 2 rough-in + fixtures | 3000 | 3250 |  |  | Smokies Plumbing | Paid in full | Capex
5 | Plumbing | Kitchen sink + supply lines | 1100 | 1200 |  |  | Smokies Plumbing | Paid in full | Capex
6 | Electrical | Kitchen circuits + outlets | 2400 | 2350 |  |  | Bright Volt | Paid in full | Capex
7 | Electrical | Bath GFCI + lighting | 1600 | 1650 |  |  | Bright Volt | Paid in full | Capex
8 | HVAC | Mini-split for upstairs | 2800 | 3100 |  |  | Mountain HVAC | Paid in full | Capex | Added zone
9 | Drywall | Kitchen + 2 baths drywall | 2200 | 2300 |  |  | Hill Drywall | Paid in full | Repair
10 | Flooring | LVP throughout (1100 sqft) | 4400 | 4600 |  |  | Floor Pros | Paid in full | Capex
11 | Flooring | Tile in baths | 1800 | 1900 |  |  | Floor Pros | Paid in full | Capex
12 | Cabinets | Kitchen cabinets (semi-custom) | 5200 | 5500 |  |  | Cabinets-N-More | Paid in full | Capex
13 | Cabinets | Bath vanities (×2) | 1800 | 1950 |  |  | Cabinets-N-More | Paid in full | Capex
14 | Countertops | Kitchen quartz | 2400 | 2600 |  |  | Stone Stop | Paid in full | Capex
15 | Countertops | Bath vanity tops | 900 | 950 |  |  | Stone Stop | Paid in full | Capex
16 | Appliances | Range / fridge / dish / micro | 3600 | 3800 |  |  | Best Buy | Paid in full | Capex
17 | Painting | Interior repaint (full) | 2400 | 2550 |  |  | Color Crew | Paid in full | Repair
18 | Fixtures | Lighting fixtures package | 1100 | 1200 |  |  | Wayfair | Paid in full | Capex
19 | Fixtures | Plumbing fixtures finish | 800 | 900 |  |  | Build.com | Paid in full | Capex
20 | Furniture | Living + bed sets | 2800 | 2900 |  |  | Self | Paid in full | Capex
21 | Decor | Wall art + accents | 900 | 950 |  |  | Self | Paid in full | Repair
22 | Outdoor | Hot tub install pad + steps | 1800 | 1850 |  |  | Hot Tub LLC | Paid in full | Capex
23 | Outdoor | Deck stain + railings | 1100 | 1200 |  |  | Color Crew | Paid in full | Repair
24 | Permits | STR permit + electrical permit | 450 | 480 |  |  | City of Gatlinburg | Paid in full | Repair
25 | Misc | Cleaning + final detail | 900 | 860 |  |  | Sparkle STR | Paid in full | Repair
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
TOTALS

## Cost Allocation
COST ALLOCATION
By-category roll-up · Capex vs Repair split · Spend by category pie
| Category | Estimate | Actual | Variance | Var % | Classification | Estimate | Actual
| Demolition |  |  |  |  | Capex
| Plumbing |  |  |  |  | Repair
| Electrical |  |  |  |  | TOTAL
HVAC
| Drywall |  |  |  |  | Capex = depreciated over time (typically 27.5 yr res / 5-15 yr via cost seg). Repair = deductible in the year incurred. Hand this split to your CPA.
Flooring
Cabinets
Countertops
Appliances
Painting
Fixtures
Furniture
Decor
Outdoor
Permits
Misc
TOTAL

## ROI Projection
ROI PROJECTION
Pre vs post-rehab nightly rate · year-1 lift · payback period · 5-yr cumulative
REVENUE INPUTS
| Pre-rehab nightly rate ($): | 145 |  | ADR before this rehab — your baseline
| Post-rehab nightly rate ($): | 185 |  | Defensible projection — pull from comp set
| Occupancy lift (% points): | 8% |  | Extra occupancy nightly — e.g., +8% = 8 pts more
| Post-rehab occupancy (%): | 55% |  | Used for 5-yr cumulative lift forecast
OUTPUTS
Total rehab spend (actual):
Year-1 revenue lift:
Payback (months):
Year-1 lift (alt: rate × occ delta):
5-YEAR PROJECTION
5-year cumulative lift:
5-year ROI on rehab:
Net 5-yr profit (lift − spend):
Why this matters: rehab dollars are an investment, not an expense. If your post-rehab ADR + occupancy lift can't pay back the spend in 60 months, the rehab is over-scoped. Right-size before you sign contractor estimates.
Questions? hello@thestrledger.com
ACQ-006 · ROI Projection

## Settings
SETTINGS
Property identity · rehab dates · contingency · year-end archive
Property name: | Smokies Ridge Cabin
Active rehab year: | 2026 | Bump in January for the next rehab. Drives any year-filtered logic.
Rehab start date: | 2026-02-01
Rehab end date (target): | 2026-04-15
Contingency %: | 15% | Default 15%. Reserve held back for surprises.
Contingency $ (auto):
Year-end Archive
Each January, copy the YTD totals from the Cost Allocation tab into the row for the closing year, then clear Budget Detail for the next rehab project.
Year | Property | Total $ | 5-yr ROI % | Notes
2024
2025
2026
2027
2028
2029
2030
Questions? hello@thestrledger.com
ACQ-006 · Settings